## Gantt Chart
PROJECT TITLE |  | San Jose's Urban Forest Project
PROJECT MANAGER |  | Martin
Sr. no | TASK TITLE | TASK OWNER | START DATE | DUE DATE | 9/4/23 - 9/8/23 |  |  |  |  | 9/11/23 - 9/15/23 |  |  |  |  | 9/18/23 - 9/22/23 |  |  |  |  | 9/25/23 - 9/29/23 |  |  |  |  | 10/2/23 - 10/6/23 |  |  |  |  | 10/9/23 - 10/13/23 |  |  |  |  | 10/16/23 - 10/20/23 |  |  |  |  | 10/23/23 - 10/27/23 |  |  |  |  | 10/30/23 - 11/3/23 |  |  |  |  | 11/6/23 - 11/10/23 |  |  |  |  | 11/13/23 - 11/17/23 |  |  |  |  | 11/20/23 - 11/24/23 |  |  |  |  | 11/27/23 - 12/1/23
[5 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13
[5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Definition and Planning (Initial Phase)
1.1 | Problem definition | Martin | 2023-09-04 | 2023-09-15 | bar: WEEK 1 M to WEEK 2 F
1.2 | Initial Report | All | 2023-09-18 | 2023-09-22 | bar: WEEK 3 M to WEEK 3 F
1.3 | Data Collection | Martin | 2023-09-22 | 2023-10-06 | bar: WEEK 3 F to WEEK 5 F
2 | Existing Research
2.1 | Understand DeepForest | William, Vaibhavi | 2023-09-25 | 2023-10-03 | bar: WEEK 4 M to WEEK 5 T
2.2 | Understand DetectTree | Manan, Yaaminie | 2023-09-25 | 2023-10-03 | bar: WEEK 4 M to WEEK 5 T
2.3 | Find Other Tools | Martin | 2023-09-25 | 2023-10-03 | bar: WEEK 4 M to WEEK 5 T
3 | Presentations
3.1 | Mid-term Presentation | All | 2023-10-05 | 2023-10-12 | bar: WEEK 5 R to WEEK 6 R
3.2 | Case Study | All | 2023-10-22 | 2023-10-31 | bar: WEEK 8 M to WEEK 9 T
4 | Project Conception and Initiation
4.1 | Data Collection Cont. | Martin | 2023-10-09 | 2023-10-20 | bar: WEEK 6 M to WEEK 7 F
4.2 | Resampling and training data selection | Vaibhavi, Yaaminie | 2023-10-20 | 2023-11-02 | bar: WEEK 7 F to WEEK 9 R
5 | Training the model
5.1 | Preparing DeepForest | All | 2023-11-03 | 2023-11-09 | bar: WEEK 9 F to WEEK 10 R
5.2 | Labeling | All | 2023-11-08 | 2023-11-10 | bar: WEEK 10 W to WEEK 10 F
5.3 | Label Fixing | Manan | 2023-11-10 | 2023-11-13 | bar: WEEK 10 F to WEEK 11 M
5.4 | Train Model | Manan | 2023-11-10 | 2023-11-20 | bar: WEEK 10 F to WEEK 12 M
6 | Testing/Evaluating the model
6.1 | Validate Model | William | 2023-11-17 | 2023-11-27 | bar: WEEK 11 F to WEEK 13 M
6.2 | Testing Model | Manan | 2023-11-08 | 2023-11-21 | bar: WEEK 10 W to WEEK 12 T
6.3 | Final Report and Presentation | All | 2023-11-21 | 2023-12-01 | bar: WEEK 12 T to WEEK 13 F